## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | South Ayrshire - DRAFT Go Live Plan
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Lesley Williams - ePos | Project Start: |  | 2023-01-02
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  |  | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2023-01-02 to 2023-02-26
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | WORK DAYS | DAYS | time axis 2023-01-02 to 2023-02-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Sample phase title block | ePOS System
| Purchase and install hardware | Kieron Gallagher | 100% | 2023-01-04 | 2023-01-13 | 8
| Create ePos system | Lesley Williams | 100% | 2023-01-13 | 2023-01-13 | 1
Girvan Go Live - golf shop only
| Provide Girvan product data | Kieron Gallagher | 100% | 2023-01-10 | 2023-01-10 | 1
| Upload product data | Lesley Williams | 100% | 2023-01-13 | 2023-01-13 | 1
| Remote Introduction for Pro shop staff (remote) - All staff from all sites | Lesley Williams | 0% | 2023-01-13 | 2023-01-13 | 1
| Back office introduction (remote) - for Kieron, Isobel and Richard | Lesley Williams | 0% | 2023-01-13 | 2023-01-13 | 1
- Training includes : Managing Products, Discounts/Specials,
| IT Setup to be completed by | SAC IT Team | 0% | 2023-01-16 | 2023-01-16 | 1
- IT Setup includes: - Install printer drivers, Install receipt printer, Install Firefox, Enable silent printing in Firefox
On-site
| ePos Training for Pro Shop staff (onsite) | Lesley Williams | 0% | 2023-01-16 | 2023-01-18 | 3 | 3
- Training includes : Tee sheet differences, Paying for a tee time, Adding items to the order, Adding a customer to the order, Taking payment, Saving an order for later, Applying discounts, Member wallet top up, Refund order, End of Day Cash Close
| Parallel running epos systems |  |  | 2023-01-16 | 2023-01-27 | 10
| Go Live Checkpoint - review/agree if on-site support is needed for w/c 30th January | Lesley & Kieron |  | 2023-01-27 | 2023-01-27 | 1
| Go Live |  |  | 2023-01-30 | 2023-01-30 | 1
| On-site support - TBD | Lesley Williams |  | 2023-01-30 | 2023-02-01
Troon Go Live - golf shop & F&B
| Provide Troon product data | Kieron Gallagher | 0% | 2023-02-06 | 2023-02-08 | 3
| Upload product data | Lesley Williams | 0% | 2023-02-10 | 2023-02-10 | 1
| F&B Menu setup | Lesley Williams | 0% | 2023-02-10 | 2023-02-10 | 1
| IT Setup to be completed by | SAC IT Team | 0% | 2023-02-10 | 2023-02-10 | 1
- IT Setup includes: - on golf shop PC - Install printer drivers, receipt printer, install Firefox and enable silent printing in Firefox for F&B - setup wifi network dedicated to F&B tills, install and configure iPad app, install receipt and kitchen printers, connect ipad app to receipt and kitchen printers.
| Parallel running epos systems for F&B w/c 13/2 |  |  | 2023-02-13 | 2023-02-17 | 5
| ePos Introduction for Pro Shop staff (onsite) | Lesley Williams | 0% | 2023-02-13 | 2023-02-15 | 3 | 3
- Training includes : Tee sheet differences, Paying for a tee time, Adding items to the order, Adding a customer to the order, Taking payment, Saving an order for later, Applying discounts, Member wallet top up, Refund order, End of Day Cash Close
| ePos Introduction for F&B staff (onsite) | Lesley Williams | 0% | 2023-02-13 | 2023-02-15 | 3 | 3
- Training includes : Paying for a tee time, Creating an Order, Adding a customer to the order, Taking payment, Food Modifiers/Notes, Hold an order, Send to Kitchen, Applying discounts, Split/Combine orders, Assign to table, Member wallet top up, Refund order, End of Day Cash Close
| Go Live Checkpoint - review/agree if on-site support is needed for w/c 30th January | Lesley & Kieron |  | 2023-02-17 | 2023-02-17 | 1
| Go Live |  |  | 2023-02-20 | 2023-02-20 | 1
| On-site support - TBD | Lesley Williams |  | 2023-02-20 | 2023-02-22
Belleisle Go Live - golf shop & F&B
| Provide Belleisle product data | Kieron Gallagher | 0% | 2023-02-21 | 2023-02-23 | 3
| Upload product data | Lesley Williams | 0% | 2023-02-24 | 2023-02-24 | 1
| F&B Menu setup | Lesley Williams | 0% | 2023-02-24 | 2023-02-24 | 1
| IT Setup to be completed by | SAC IT Team | 0% | 2023-02-24 | 2023-02-24 | 1
- IT Setup includes: - on golf shop PC - Install printer drivers, receipt printer, install Firefox and enable silent printing in Firefox for F&B - setup wifi network dedicated to F&B tills, install and configure iPad app, install receipt and kitchen printers, connect ipad app to receipt and kitchen printers.
| Parallel running epos systems for F&B w/c 17/2 - May not be required |  |  | 2023-02-27 | 2023-03-03 | 5
| ePos Introduction for Pro Shop staff (onsite?) | Lesley Williams | 0% | 2023-02-27 | 2023-02-27 | 1 | 1
- Training includes : Tee sheet differences, Paying for a tee time, Adding items to the order, Adding a customer to the order, Taking payment, Saving an order for later, Applying discounts, Member wallet top up, Refund order, End of Day Cash Close
| ePos Introduction for F&B staff (onsite?) | Lesley Williams | 0% | 2023-02-27 | 2023-02-27 | 1
- Training includes : Paying for a tee time, Creating an Order, Adding a customer to the order, Taking payment, Food Modifiers/Notes, Hold an order, Send to Kitchen, Applying discounts, Split/Combine orders, Assign to table, Member wallet top up, Refund order, End of Day Cash Close
| Go Live Checkpoint - review/agree if on-site support is needed for w/c 30th January | Lesley & Kieron |  | 2023-03-03 | 2023-03-03 | 1
This is an empty row | Go Live |  |  | 2023-03-06 | 2023-03-06 | 1 | 1
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | On-site support - TBD | Lesley Williams |  | 2023-03-06 | 2023-03-08
Dalmilling Go Live - golf shop
Dalmilling setup is identical to Girvan and could be set up immediately after Girvan if appropriate.
| Provide Dalmilling product data | Kieron Gallagher | 0% | 2023-02-21 | 2023-02-23 | 3
| Upload product data | Lesley Williams | 0% | 2023-02-24 | 2023-02-24 | 1
| F&B Menu setup | Lesley Williams | 0% | 2023-02-24 | 2023-02-24 | 1
| IT Setup to be completed by | SAC IT Team | 0% | 2023-02-24 | 2023-02-24 | 1
- IT Setup includes: - Install printer drivers, receipt printer, install Firefox and enable silent printing in Firefox
| Parallel running epos systems w/c 17/2 - may not be required |  |  | 2023-02-27 | 2023-03-03 | 5
| ePos Introduction for Pro Shop staff (onsite?) | Lesley Williams | 0% | 2023-02-27 | 2023-02-27 | 1 | 1
- Training includes : Tee sheet differences, Paying for a tee time, Adding items to the order, Adding a customer to the order, Taking payment, Saving an order for later, Applying discounts, Member wallet top up, Refund order, End of Day Cash Close
| ePos Introduction for F&B staff (onsite?) | Lesley Williams | 0% | 2023-02-27 | 2023-02-27 | 1
- Training includes : Paying for a tee time, Creating an Order, Adding a customer to the order, Taking payment, Food Modifiers/Notes, Hold an order, Send to Kitchen, Applying discounts, Split/Combine orders, Assign to table, Member wallet top up, Refund order, End of Day Cash Close
| Go Live Checkpoint - review/agree if on-site support is needed for w/c 30th January | Lesley & Kieron |  | 2023-03-03 | 2023-03-03 | 1
This is an empty row | Go Live |  |  | 2023-03-06 | 2023-03-06 | 1 | 1
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | On-site support - TBD | Lesley Williams |  | 2023-03-06 | 2023-03-08
Insert new rows ABOVE this one