## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | The Leatherhead - DRAFT Go Live Plan
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Steph Rennie - Teesheet & Payments Lesley Williams/Martin Fitzpatrick - ePos | Project Start: |  | 2022-09-26
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  |  | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-09-26 to 2022-11-20
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | WORK DAYS | DAYS | time axis 2022-09-26 to 2022-11-20
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Tee Sheet
| Create a new tee sheet system | Steph Rennie | 100% | 2022-09-26 | 2022-09-26 | 1
- Members booking module/app - Visitor Booking module - SMS Module
| Transfer Member Data - Club to provide CSV file | Dominic Hill | 100% | 2022-09-30 | 2022-09-30 | 1
| Tee Sheet training - member registration email | Steph Rennie | 0% | 2022-09-29 | 2022-09-29 | 1
| Transfer tee sheet bookings | Steph & Lesley | 50% | 2022-10-07 | 2022-10-07 | 1
- Park Room - Perry Room - Tee sheet
| Agree cutover to new tee sheet | Lesley & Dominic | 0% | 2022-10-10 | 2022-10-10 | 1
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | BRS Payments
| Provide director details and relevant documentation | Dominic Hill | 100% | 2022-09-27 | 2022-09-29 | 3 | 3
| Create BRS Payments system | Steph Rennie | 100% | 2022-09-30 | 2022-09-30 | 1 | 1
BRS Memberships
| Create BRS Memberships system | Lesley Williams | 100% | 2022-09-30 | 2022-09-30 | 1
| Syncing member data between teesheet & memberships | Lesley Williams | 100% | 2022-09-30 | 2022-09-30 | 1
Distribution
| Setup Facility | Steph | 0% | 2022-10-11 | 2022-10-11 | 1
| Agree cutover for distribution | Steph & Dominic | 0% | 2022-10-21 | 2022-10-21 | 1
Sample phase title block | ePOS System
| Provide recommended hardware list | Lesley Williams | 100% | 2022-09-13 | 2022-09-13 | 1 | 1
| Purchase and install hardware | Dominic Hill | 60% | 2022-09-14 | 2022-09-30 | 13
| Provide product data from existing epos system | Dominic Hill | 0% | 2022-10-19 | 2022-10-24 | 4
| Create ePos system | Lesley Williams | 0% | 2022-10-10 | 2022-10-10 | 1
| Upload product data | Lesley Williams | 0% | 2022-10-25 | 2022-10-25 | 1
| Provide member wallet balances | Dominic Hill | 0% | 2022-10-26 | 2022-10-26 | 1
| Upload member wallet balances | Lesley Williams | 0% | 2022-11-01 | 2022-11-01 | 1
| ePos Introduction for Pro Shop staff | Lesley Williams | 0% | 2022-10-26 | 2022-10-26 | 1 | 1
| ePos Introduction for Bar/Restaurant staff | Lesley Williams | 0% | 2022-10-28 | 2022-10-28 | 1 | 1
| ePos Introduction for Back office staff | Lesley Williams | 0% | 2022-10-26 | 2022-10-26 | 1 | 1
| iPad Setup | Dominic Hill | 0% | 2022-10-28 | 2022-10-28 | 1
| Go Live Checkpoint | Lesley & Dominic |  | 2022-10-28 | 2022-10-28 | 1
| Convert tee sheet to ePos tee sheet | Lesley & Martin |  | 2022-10-10 | 2022-10-10 | 1
Sample phase title block | On-Site ePos Training & Go Live
| ePos Training for Pro Shop Staff | Lesley Williams | 0% | 2022-11-02 | 2022-11-02 | 1 | 1
- Training includes : Tee sheet differences, Paying for a tee time, Adding items to the order, Adding a customer to the order, Taking payment, Saving an order for later, Applying discounts, Member wallet top up, Refund order, End of Day Cash Close
| ePos go live for Pro Shop Staff | Lesley & Dominic | 0% | 2022-11-03 | 2022-11-03 | 1
| ePos Training for Bar/Restaurant Staff | Lesley & Martin | 0% | 2022-11-04 | 2022-11-04 | 1
- Training includes : Paying for a tee time, Creating an Order, Adding a customer to the order, Taking payment, Food Modifiers/Notes, Hold an order, Send to Kitchen, Applying discounts, Split/Combine orders, Assign to table, Member wallet top up, Refund order, End of Day Cash Close
| ePos go live for Bar/Restaurant Staff | Lesley & Dominic | 0% | 2022-11-07 | 2022-11-07 | 1 | 1
| ePos Training for Back Office Staff | Lesley & Martin | 0% | 2022-11-02 | 2022-11-02 | 1
- Training includes : Managing Products, Discounts/Specials,
| ePos go live for Back Office Staff | Lesley & Dominic | 0% | 2022-11-02 | 2022-11-02 | 1 | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one